## Read Me
TrustWall — 90-Day Content Calendar
Companion to MARKETING_PLAN.md. Cheap (<$100/mo), Claude-powered. Beachhead niche: coaches.
HOW TO USE
1 | Work the '90-Day Calendar' tab top to bottom, one week at a time. Each row is one task.
2 | Tasks marked with a 'Prompt' reference have paste-ready Claude prompts in the 'Prompt Library' tab.
3 | Fill the 'Status' column (Todo / Doing / Done). Log results each Friday in the 'Metrics' tab.
4 | You are the strategist + voice + fact-checker. Claude drafts, researches, and repurposes.
5 | Run ONE experiment at a time. Master Tier-1 channels before adding anything new.
TABS
90-Day Calendar | Week-by-week task list across all channels (the core plan).
Weekly Loop | The repeatable ~7.5 hr/week cadence to run after day 90.
Prompt Library | 9 paste-ready Claude prompts (A–I) for every recurring task.
Budget | Line-item monthly spend — stays under $100/mo.
Metrics | 90-day targets + a weekly tracker with an auto activation-rate formula.
CHANNEL KEY
SEO | Articles: pain-point clusters, comparison/'vs' pages, template/tool pages.
Social | Build-in-public posts on X + LinkedIn.
Community | Value-first help in Skool / Facebook groups / subreddits / Indie Hackers.
Outreach | Personalized, intent-based DMs + white-glove onboarding.
Launch | Product Hunt + BetaList + Firsto + Reddit + Indie Hackers (staggered).
Dogfood / Email / Review | Use TrustWall on yourself; lifecycle email; weekly review.

## 90-Day Calendar
Week | Dates (2026) | Phase | Channel | Task | Claude asset | Est. hrs | Cost | KPI / Target | Status
W1 | Jun 8–14 | 1 · Foundation | Setup | Lock the one-liner + the 'vs Testimonial.to' positioning story | Prompt A & C | 1 | $0 | Messaging locked
W1 | Jun 8–14 | 1 · Foundation | Setup | Set up Google Search Console + analytics; clean up X & LinkedIn profiles | — | 2 | $0 | Tracking live
W1 | Jun 8–14 | 1 · Foundation | Dogfood | Stand up your own TrustWall wall; ask 5 friendly coaches for a testimonial | Prompt F | 2 | $0 | 5 requests sent
W1 | Jun 8–14 | 1 · Foundation | SEO | Publish cornerstone #1: 'TrustWall vs Testimonial.to (for coaches)' | Prompt C | 3 | $0 | 1 page live
W1 | Jun 8–14 | 1 · Foundation | Email | Write + switch on the 4-email onboarding sequence | Prompt G | 2 | $0 | Sequence sending
W1 | Jun 8–14 | 1 · Foundation | Social | First 5 build-in-public posts (the launch story) | Prompt D | 1 | $0 | 5 posts
W2 | Jun 15–21 | 1 · Foundation | SEO | Cornerstone #2: 'How coaches get Google star ratings (without slowing their site)' | Prompt A → B | 3 | $0 | 1 page live
W2 | Jun 15–21 | 1 · Foundation | SEO | Keyword map: 15–20 coach pain-point keywords → cluster plan | Prompt A | 1.5 | $0 | Keyword map done
W2 | Jun 15–21 | 1 · Foundation | Community | Join 3 coach communities (Skool / Facebook / subreddits); introduce yourself, no pitch | — | 1 | $0 | 3 joined
W2 | Jun 15–21 | 1 · Foundation | Dogfood | Publish your Wall of Love; collect 5 real testimonials | Prompt F | 1 | $0 | 5+ live
W2 | Jun 15–21 | 1 · Foundation | Social | 5 build-in-public posts incl. 1 'view-source' wedge demo | Prompt D | 1 | $0 | 5 posts
W3 | Jun 22–28 | 1 · Foundation | SEO | Article 3: 'How to ask clients for a testimonial (email scripts + templates)' | Prompt B | 2.5 | $0 | 1 page live
W3 | Jun 22–28 | 1 · Foundation | SEO | Article 4 (template/tool page): 'Free wall-of-love + request email templates' | Prompt B | 2.5 | $0 | 1 page live
W3 | Jun 22–28 | 1 · Foundation | Community | 5 value-first answers across communities | Prompt E | 1 | $0 | 5 helpful posts
W3 | Jun 22–28 | 1 · Foundation | Outreach | White-glove onboard your first 3–5 users by hand | Prompt F | 2 | $0 | 3–5 onboarded
W3 | Jun 22–28 | 1 · Foundation | Social | 5 build-in-public posts | Prompt D | 1 | $0 | 5 posts
W3 | Jun 22–28 | 1 · Foundation | Review | Phase 1 exit check + plan Phase 2 | — | 0.5 | $0 | Exit criteria met
W4 | Jun 29–Jul 5 | 2 · Engine | SEO | 2 articles: 'Senja alternative for coaches' (comparison) + 1 pain-point | Prompt C, B | 4 | $0 | 2 pages live
W4 | Jun 29–Jul 5 | 2 · Engine | Social | 5 build-in-public posts | Prompt D | 1 | $0 | 5 posts
W4 | Jun 29–Jul 5 | 2 · Engine | Community | 5 value-first answers + 1 Indie Hackers milestone post | Prompt E, D | 1.5 | $0 | 6 posts
W4 | Jun 29–Jul 5 | 2 · Engine | Outreach | 5–10 personalized DMs to intent signals | Prompt F | 1.5 | $0 | 5–10 DMs
W4 | Jun 29–Jul 5 | 2 · Engine | Repurpose | Turn the week's best article into a thread + posts | Prompt I | 0.5 | $0 | 1 → many
W5 | Jul 6–12 | 2 · Engine | SEO | 2 articles (pain-point cluster) | Prompt B | 4 | $0 | 2 pages live
W5 | Jul 6–12 | 2 · Engine | Social | 5 build-in-public posts | Prompt D | 1 | $0 | 5 posts
W5 | Jul 6–12 | 2 · Engine | Community | 5 value-first answers | Prompt E | 1 | $0 | 5 posts
W5 | Jul 6–12 | 2 · Engine | Outreach | 5–10 personalized DMs + white-glove onboarding | Prompt F | 1.5 | $0 | 5–10 DMs
W5 | Jul 6–12 | 2 · Engine | Referral | Add a light referral ask to happy free users | Prompt G | 0.5 | $0 | Ask live
W6 | Jul 13–19 | 2 · Engine | SEO | 2 articles (1 comparison + 1 template page) | Prompt C, B | 4 | $0 | 2 pages live
W6 | Jul 13–19 | 2 · Engine | Launch prep | Build launch waitlist landing page + start teasing it | Prompt D | 1.5 | $0 | Waitlist live
W6 | Jul 13–19 | 2 · Engine | Social | 5 build-in-public posts | Prompt D | 1 | $0 | 5 posts
W6 | Jul 13–19 | 2 · Engine | Community | 5 value-first answers | Prompt E | 1 | $0 | 5 posts
W6 | Jul 13–19 | 2 · Engine | Outreach | 10 personalized DMs | Prompt F | 1.5 | $0 | 10 DMs
W7 | Jul 20–26 | 2 · Engine | SEO | 2 articles | Prompt B | 4 | $0 | 2 pages live
W7 | Jul 20–26 | 2 · Engine | Content | Draft first case study from a white-glove user | Prompt B | 1.5 | $0 | Draft done
W7 | Jul 20–26 | 2 · Engine | Launch prep | Prep Product Hunt assets (tagline, gallery, description, first comment) | Prompt D | 1.5 | $0 | Assets ready
W7 | Jul 20–26 | 2 · Engine | Social | 5 build-in-public posts incl. waitlist push | Prompt D | 1 | $0 | 5 posts
W7 | Jul 20–26 | 2 · Engine | Outreach | 10 personalized DMs | Prompt F | 1.5 | $0 | 10 DMs
W8 | Jul 27–Aug 2 | 2 · Engine | SEO | 2 articles | Prompt B | 4 | $0 | 2 pages live
W8 | Jul 27–Aug 2 | 2 · Engine | Launch prep | Finalize launch email + directory blurbs (BetaList, Firsto) | Prompt G, D | 1.5 | $0 | Assets final
W8 | Jul 27–Aug 2 | 2 · Engine | Community | 5 value-first answers + Indie Hackers 'launching next week' post | Prompt E, D | 1.5 | $0 | 6 posts
W8 | Jul 27–Aug 2 | 2 · Engine | Outreach | 10 personalized DMs | Prompt F | 1.5 | $0 | 10 DMs
W8 | Jul 27–Aug 2 | 2 · Engine | Review | Phase 2 exit check; confirm waitlist + assets ready | — | 0.5 | $0 | Exit criteria met
W9 | Aug 3–9 | 3 · Launch & Scale | Launch | Product Hunt launch (12:01am PST, Tue–Thu); reply to every comment <4h for 24–48h | Prompt D | 4 | $0 | PH live, all comments answered
W9 | Aug 3–9 | 3 · Launch & Scale | Launch | Stagger submissions: BetaList, Firsto, relevant directories | — | 1 | $0 | 3+ submissions
W9 | Aug 3–9 | 3 · Launch & Scale | Launch | Reddit problem-statement post + Indie Hackers 'we launched' | Prompt E, D | 1 | $0 | 2 posts
W9 | Aug 3–9 | 3 · Launch & Scale | Email | 'We're live' email to list + waitlist | Prompt G | 0.5 | $0 | Sent
W9 | Aug 3–9 | 3 · Launch & Scale | Social | Launch-day posts on X + LinkedIn | Prompt D | 1 | $0 | Posts live
W10 | Aug 10–16 | 3 · Launch & Scale | Content | Publish launch case study: 'How [coach] got Google stars in a week' | Prompt B | 2.5 | $0 | 1 case study live
W10 | Aug 10–16 | 3 · Launch & Scale | SEO | 1–2 articles continuing clusters | Prompt B | 3 | $0 | 1–2 pages
W10 | Aug 10–16 | 3 · Launch & Scale | Analyze | Review which channel converted best at launch; double down | — | 1 | $0 | Decision made
W10 | Aug 10–16 | 3 · Launch & Scale | Outreach | 10 personalized DMs | Prompt F | 1.5 | $0 | 10 DMs
W10 | Aug 10–16 | 3 · Launch & Scale | Social | 5 posts incl. launch results recap | Prompt D | 1 | $0 | 5 posts
W11 | Aug 17–23 | 3 · Launch & Scale | SEO | 2 articles (double down on best-performing type) | Prompt B, C | 4 | $0 | 2 pages
W11 | Aug 17–23 | 3 · Launch & Scale | Content | 2nd case study / testimonial spotlight | Prompt B | 1.5 | $0 | 1 piece
W11 | Aug 17–23 | 3 · Launch & Scale | Community | 5 value-first answers | Prompt E | 1 | $0 | 5 posts
W11 | Aug 17–23 | 3 · Launch & Scale | Outreach | 10 personalized DMs | Prompt F | 1.5 | $0 | 10 DMs
W11 | Aug 17–23 | 3 · Launch & Scale | Experiment | Run ONE paywall or headline experiment | — | 0.5 | $0–15 | 1 experiment
W12 | Aug 24–30 | 3 · Launch & Scale | SEO | 2 articles | Prompt B | 4 | $0 | 2 pages
W12 | Aug 24–30 | 3 · Launch & Scale | Social | 5 posts + a 90-day recap thread | Prompt D, I | 1 | $0 | 6 posts
W12 | Aug 24–30 | 3 · Launch & Scale | Outreach | 10 personalized DMs | Prompt F | 1.5 | $0 | 10 DMs
W12 | Aug 24–30 | 3 · Launch & Scale | Review | 90-day review vs targets; lock the weekly loop | — | 1 | $0 | Loop locked
W12 | Aug 24–30 | 3 · Launch & Scale | Plan | Decide niche #2 (course creators) expansion | Prompt H | 0.5 | $0 | Decision made
|  |  |  | TOTAL estimated hours → |  | 105

## Weekly Loop
The repeatable weekly loop (run after day 90)
~7.5 focused hours/week, mostly with Claude. Consistency compounds; sprints don't.
Activity | Cadence | Est. hrs | Claude asset | KPI
Publish 2 articles (pain-point / comparison / template) | Weekly | 3 | Prompt A → B / C | 2 indexed pages
5 build-in-public posts (X + LinkedIn) | Weekly | 1 | Prompt D | Reach + signups
~5 community touchpoints (help first) | Weekly | 1 | Prompt E | Profile clicks
~10 personalized DMs to intent signals | Weekly | 1 | Prompt F | Reply rate
1 case study / customer win, repurposed | Weekly | 1 | Prompt B / I | 1 asset → many
Weekly review + queue next week | Weekly | 0.5 | — | Metrics updated
TOTAL / week |  | 7.5

## Prompt Library
Claude Prompt Library
Paste-ready. Always supply your first-hand take + screenshots, and fact-check before publishing. Never fabricate testimonials, names, numbers, or stats.
Ref | Name | When to use | Prompt (paste into Claude)
A | SEO content brief | Before writing any article | You're an SEO strategist for TrustWall, a testimonial tool for coaches whose wedge is SEO-positive embeds (server-rendered review text + schema.org markup that earns Google star ratings, on the $19 plan vs competitors' $80 tier). Target keyword: [keyword]. Give me: search intent, who's searching and why, an outline (H2/H3) that genuinely answers it, the angle only we can write from, 3 title options, a meta description, and 4 internal-link ideas. Don't write the article yet.
B | Article draft (your voice) | To draft any article/case study | Write the article from this brief: [paste brief]. Audience: solo coaches, not technical. Voice: clear, warm, concrete, no hype, no fluff. ~1,200 words. Use real specifics; where you'd need a fact/number/screenshot I should supply, mark it [FILL: …]. Never invent stats, customer names, or testimonials. End with one soft CTA to start free.
C | Comparison / 'vs' page | High-intent bottom-funnel pages | Draft a 'TrustWall vs Testimonial.to' page for coaches. Use ONLY these verified facts: [paste the competitor table + notes]. Be fair — note where they're stronger. Center the comparison on what a coach actually cares about: Google star ratings, page speed, price, consent/automation. Include a comparison table and an honest 'who should pick which' section. Mark anything you're unsure of as [VERIFY]. No fabricated claims.
D | Build-in-public post / thread | Daily social + launch posts | Turn this into (1) an X thread and (2) a LinkedIn post, in a build-in-public founder voice — honest, specific, a little vulnerable, no growth-hacky hype: [paste the update / metric / shipped feature / screenshot description]. Hook in the first line. One clear takeaway. Soft, optional mention of TrustWall.
E | Community reply (value-first) | Answering community questions | Here's a post from [community] asking [paste]. Write a genuinely helpful reply that solves their problem first. Mention TrustWall only if directly relevant, once, as 'one option' — never salesy. Match the community's casual tone.
F | Intent-based DM | Personalized outreach + dogfood asks | This person publicly posted: [paste]. Write a short, human DM (3–4 sentences) that references their specific situation, offers real help, and only mentions TrustWall if it genuinely fits. No template feel, no pitch energy. Goal is a conversation, not a click.
G | Lifecycle / onboarding email | Onboarding, nudges, launch email | Write a [welcome / 48h-nudge / embed-code / soft-upgrade] email for a coach who just signed up free. Goal: get them to collect their first testimonial (our activation metric) / embed it / see Google stars. <120 words, one CTA, warm and concrete. Give me 2 subject lines.
H | Niche pivot | Expanding past coaches | Rewrite this coach-targeted asset for [course creators / consultants]: [paste]. Swap vocabulary, examples, and pain points to fit them. Keep the wedge and structure. Flag anything that no longer applies.
I | Repurpose 1 → many | Squeeze more from each asset | From this article [paste/link], give me: 1 X thread, 1 LinkedIn post, 3 short community-answer snippets, and 2 email subject lines. Keep my voice. No fabricated claims or stats.

## Budget
Monthly Budget (target: under $100/mo)
Everything works at $0 if fully organic; optional tools just save time. The expensive input is consistency, not cash.
Item | Tool | Low ($/mo) | High ($/mo) | Notes
AI execution engine | Claude | 0 | 20 | Drafting, research, repurposing — the core engine
Email sending | Resend (free tier) | 0 | 0 | Ample at this volume
Analytics | PostHog / Plausible (free tier) | 0 | 9 | Funnel + activation tracking
Search data | Google Search Console + 1 light keyword tool (optional) | 0 | 30 | Keyword research
Social scheduling | Manual or free-tier scheduler | 0 | 15 | Optional time-saver
Launch / directories | Product Hunt, BetaList, Firsto, Reddit, Indie Hackers | 0 | 0 | Free
Experiment buffer | One paid test at a time | 0 | 15 | Optional
| TOTAL | 0 | 89
| Target ceiling |  | 100

## Metrics
Metrics & Weekly Tracker
North-star = activation (free users who collected their first testimonial). Judge yourself on leading indicators early; lagging numbers follow.
90-DAY TARGETS
Metric | 90-day target | Type
Articles published & indexed | 12–20 | Leading / output
Free signups | 50–100 | Lagging
Activation rate (collected 1st testimonial) | 40%+ | NORTH-STAR
Paying customers (Pro $19 / Studio $39) | 5–10 | Lagging
MRR | $100–300 | Lagging
Launch executed (PH + 2 more surfaces) | Yes | Milestone
WEEKLY TRACKER (fill each Friday — activation % is automatic)
Week | Articles | Social posts | Community | DMs | Signups | Activated | Activation % | Paying | MRR ($)
W1 Jun 8 | [6 empty] | -
W2 Jun 15 | [6 empty] | -
W3 Jun 22 | [6 empty] | -
W4 Jun 29 | [6 empty] | -
W5 Jul 6 | [6 empty] | -
W6 Jul 13 | [6 empty] | -
W7 Jul 20 | [6 empty] | -
W8 Jul 27 | [6 empty] | -
W9 Aug 3 | [6 empty] | -
W10 Aug 10 | [6 empty] | -
W11 Aug 17 | [6 empty] | -
W12 Aug 24 | [6 empty] | -
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0